Digitization project diary (for the report)

February 11, 3 PM – 5 PM

Start-up meeting (Cecilia, Clara, Johanna)

Common read through of project assignment. Review and decision to digitize and encode a 17th-century funeral poem using the TEI standard with the goal of producing a scholarly reliable and machine-readable text edition. The idea emerged from Johanna’s doctoral research, during which she identified a suitable poem preserved at the Humanities Library, Gothenburg University Library (GUL).

Next step: Johanna to contact GUL and arrange meetings with the special collection’s librarian as well as staff member responsible for digitization.

Questions: Can we use image captioning equipment at the library? Are there any technical and/or meta language demands from GUL?

March 2, 2 PM – 5.30 PM

Meeting with Kristina Sevo, Special Collections, Manuscripts and Archives, at the Humanities Library, Gothenburg University Library (Cecilia, Clara, Johanna)

Guided tour of the closed stacks. The funeral poem, previously identified by Johanna can’t be found. Kristina presents other rare prints of 17th-century funeral poems (epicedium is perhaps a better term?). We select five prints of funeral poems about women. These documents must be catalogued before image capturing can be carried out.

March 10-13, (Borås workshops)

(Cecilia, Johanna)

Decision on naming strategy for images (scalable).

Discussions on TEI document set-up (Johanna set-up document and send out invitations)

March 17, 10 AM – 3 PM

Image captioning at GUL, Per Örtenblad, mfl Cecilia, Clara, Johanna)

We carry out three different forms of image captioning for each of the five select funeral poems. First using the Zeutschel flatbed scanner, then a fixed digital camera with controlled lighting and finally an older flatbed scanner.

The Zeutschel flatbed scanner is the standard equipment used for digitization projects at the library. Interestingly, the image produced with digital camera reveled more details, such as water marks and embossing, which were not visible in the Zeutschel scanner.

(Här utökar vi med foton som jag tagit och lägger till tekniska detaljer)

Next step: Image files to be sent to us via a download link, the library does not allow external equipment to be connected for security reasons. Each of us is responsible for transcribing and encoding one document. However, we first need to agree on a common TEI encoding scheme and that is the purpose for our next meeting.

April 1, 4 PM

(Cecilia, Clara, Johanna)

Discussions of 17th Century Swedish language, letters, spelling, grammar and “false friends”. Initial discussion on TEI encoding scheme.

Next step: Cecilia and Clara to finish transcribing their documents and begin TEI encoding.

April 7, 8.30 AM– 12 AM

(Cecilia, Clara, Johanna)

Review and edit of transcripts. Cecilia and Clara both used Transkribus to generate initial drafts of the transcriptions. Johanna preferred to do her by hand. While the AI-supported software proved useful, several limitations became apparent. It struggles to reliable distinguish between 17th century å and ä, and frequently confuses f, the long s (ſ) and k. Decorated initials, that can be hard to read for the untrained eye, are commonly misread. Words written in proximity tend to merge incorrectly.  There are also further discussions on what should be included in the TEI Editorial Notes.

April 17

(Cecilia, Clara, Johanna)

We review, compare and make the coding consistent in all three (four documents). There’s a discussion on whether “Publisher” that implies place of printing also could imply place of reading the text for the first time (prior to printing it).

May 5, 8.00-14.00

(Cecilia, Clara, Johanna)

Review of TEI code and inclusion of codes to facilitate transformation to HTML, for example “facsimile”. Discussion on web layout and structure. We decide on a color scheme, basic layout and to include illustrations (from the printed documents) as a decorative element on the start page. A short introductory text to the website is produced.

There are inconsistencies (variations) in spelling of names across different types of sources. For example, Gunborg Kinnmund and Gunborg Kinninmundt. Sine the spelling of the Swedish language was not standardized in the seventeenth century, preserve theses inconsistencies as they appear in the original sources.

During this work meeting we also clean up our local folders and remove image files and documents no longer in used.

Next step: Proofreading and fix a problem in the TEI coding where two Headlines appear on the same pace. Johanna finds a solution and implements final markup of the presentation site.

Rapporten ska innehålla:

- En grundlig dokumentation av det metodiska arbete gruppen har utfört och de åtgärder som vidtagits (cirka 1/3 av rapporten, kom ihåg att detaljerad teknisk dokumentation kan placeras i en bilaga som inte ingår i ordantalet). Glöm inte frågan om hur långsiktigt bevarande kan säkras.

Har påbörjats här ovan

- En estimering av tidsåtgången för de olika faserna i projektet (till exempel i form av en tabell) och med tillägget av vad en fortsättning skulle fordra.

Kan sammanställas baserat på ovan och egen tid

- En kort redogörelse för de synpunkter som lämnats av avnämare/uppdragsgivare, i de fall sådana finns (vilket är bra)

Har vi något här? Annat än att biblioteket agerar med att tillgängliggöra (katalogisera)dokument digitalt utifrån förfrågningar)

- En argumentation för projektets relevans för kulturarvsbevarande i allmänhet.

Bevara vårt gemensamma kulturarv. Digitalisering gör vårt kulturarv mer öppet och tillgängligt för alla oavsett geografisk plats.

Tillgängliggöra en primärkälla för forskning. Dokumenten ger inblick i människors liv, hur samhället såg ut, förhållande till religion. Forskningsvärde för flera discipliner.

Dokumenten är också intressant ur ett språkforskningsperspektiv – visar hur språket användes innan stavning och grammatik standardiserade – språkförändring och dialekter

Digitalisering gör det möjligt att dokument kan analyseras med ny teknik och metoder till exempel AI, databassökning. Möjliggör tvärvetenskaplig och internationell forskning – jämföra material från olika delar av världen

Bevarande av sköra dokument (fast tydligen mår också dokumenten bra av att vidröras och användas)

- En kritisk analys/argumentation för gruppens val och de metoder som använts i arbetet på en högre abstraktionsnivå än det tekniska/konkreta. Argumentation måste vara förankrad i litteratur, främst kurslitteraturen (särskilt den forskningsbaserade delen av litteraturen).

TEI: internationell forskning, tvärvetenskap osv (TEI manifestet)

Massdigitalisering och kritisk digitalisering (vår upplevelse av det universitetet gör och vad vi valde att göra. (anknyta till Mats text) Humanistiska bibliotekets arbetsbörda vs process. Hur etablerat är egentligen

Bildval: det vi upptäckte genom tre olika bildfångsmetoder (vattenstämplar osv)

Val att presentera språket som det är (autenticitet, så nära originalet som möjligt, bevarar historiskt och kulturellt värde, minimalt med tolkningar – ”så här skrev och uttryckte sig faktiskt folk”. Modernisering av språket kan ibland förändra betydelsen eller nyanser i texten. Minskar risken för misstolkningar

Vi har intagit ett realistiskt perspektiv (vetenskapsteoretisk källa) - återge dokumentet så exakt som möjligt.

Källkritisk transparens.

- Slutsatser (såsom lärdomar, rekommendationer för framtida arbete, skalbarhet etc.).

Att uppnå konsekvens (i kodning och angreppssätt är en utmaning för flera som ) utifrån valmöjligheter

Skalbart: stor tidsåtgång för detta detaljnivå vilket inte (utifrån samhällets begränsade resurser ) kanske inte är hållbart.

Möjligheten att få en inblick i – och komma nära – människors öden i en svunnen tid.